Project/ Programme Technical Report Guidance and Template

Contents

PART 1: GENERAL NARRATIVE REPORT (every 6 months, recommended 7-8 pages)	2

1.	General Information about the Project	2

2.	Key Outcomes and impacts achieved (approx. 1-2 pages)	2

3.	Effective Implementation of Work Plans and Budgets (max. 1 page).	3

4.	Risk Management (max. 1 page).	3

5.	Environmental and Social Safeguards (max. 1 page).	3

6.	Learning and Adaptations needed (approx. 2 page)	4

6.1 Reflection	4

6.2 Lessons Learned	4

6.3 Adaptive Management	4

PART 2: MONITORING REPORT (every 12 mths for projects/ programmes >€100K p.a.)	5

Project/ Programme Technical Report Guidance and Template

# PART 1: GENERAL NARRATIVE REPORT (every 6 months, recommended 7-8 pages)

Writing a good quality report

This summary report supports team reviews and is required to keep the WWF network informed of progress and learning. Before you start writing, read this additional guidance.  Need some inspiration? Find good example reports here or find useful tips and tricks in this support and FAQ document. If you are reporting for a project/ programme that consists of several closely related (sub)projects, it is recommended to consolidate your reporting into one TPR.

How to use this TPR format?

Section headings express the essence of each section and bullets underneath provide guidance. Remove the description of each section before finalising your report. Use of visualisations, graphics and tables is encouraged.

For the 12 month report, it is recommended that larger projects (>€100K p.a.) should complete the Monitoring report (Part 2) before completing Part 1.

## General Information about the Project

| Project/ Programme Name: |  |
| --- | --- |
| Project/Programme CPM Database Number(s): |  |
| Reporting Period: |  |
| Project/Programme Start Date (FY): |  |
| Report Completed by: |  |
| Date Report Completed (MM/YR): |  |

## Key Outcomes and impacts achieved (approx. 1-2 pages)

- Based on an analysis of monitoring data, describe your progress towards reaching the impacts (goals) and outcomes (objectives) of your theory of change/ logframe. The progress reported should be additional to that described in the previous reports.

- Explain the role of WWF and partners in achieving these results.

- Mention any unexpected changes (negative and/or positive) as a consequence of your activities

## Effective Implementation of Work Plans and Budgets (max. 1 page).

- Briefly summarise whether progress against major activities is going according to schedule. If not, why not?  (If a primary donor requires detailed reporting vs workplan or other evidence, include this in an annex).

- Highlight any problem areas. Underlying issues and any remedial actions must be reflected in section 6.

- State the burn-rate (i.e. [Actual / Planned Expenditure] x 100). Relate this to any major variances in your financial report as well as to the (approximate) % implementation of your work plan.

## Risk Management (max. 1 page).

Provide a link to your updated project/ programme risk register (if available) and confirm whether this has been reviewed by relevant team members. Briefly summarise:

- Changes in the risks identified

- New risks

- Whether the project has been able to mitigate risks, especially for high risks

Internal risks:  factors that may affect success such as limited human resources, capacity or management capabilities, ownership and failure to sustain results.

External risks: conditions outside the project which could have an influence on the implementation and achievement of results. External risks could be related to unexpected political, institutional, economic, environmental, social or technological conditions.

## Environmental and Social Safeguards (max. 1 page).

- ESSF process: Summarise the status of the ESSF process in terms of progress of screening, mitigation planning, implementation and monitoring. (This may be for the project and/ or the related landscape(s) as applicable).

- ESSF progress: Where an ESSF mitigation workplan is being implemented, briefly summarise progress against the major activities related to substantive standards (e.g. work with Indigenous Peoples). Provide a link to the updated ESSF mitigation workplan (if available).

- Make sure to include any overall ESSF reflections and adaptive actions in section 6.

## Learning and Adaptations needed (approx. 2 page)

### 6.1 Reflection Reflecting on the progress towards your Theory of Change, Workplan, Risk management and ESSF mitigation, summarise which factors have affected delivery of results positively or negatively. Internal factors could be management processes, capacity, donor support, funding, and external factors could be stakeholder behaviour or engagement, partner collaboration or leverage as well as (changes in) the political, economic and environmental context. - Identify any new challenges/ concerns or opportunities. - Where internal challenges or weaknesses remain that were already identified in previous reports, explain why this is the case.

Positive factors (internal or external) - ... - ... Negative factors (internal or external) - … - ...

### 6.2 Lessons Learned Analysing the factors above, what has the project team learned?

- [Lessons learned 1] - [lessons learned 2] - [……]

### 6.3 Adaptive Management Based on what you have learned, how will you adapt your Theory of Change, risk management, ESSF mitigation and/or workplan/budget? Note any major changes needed to assumptions, objectives, strategies and/or financial investments.

Adaptive actions done or needed - [adaptation 1] - [adaptation 2] - [……]

# PART 2: MONITORING REPORT (every 12 mths for projects/ programmes >€100K p.a.)

Submit as Excel (available here), Word table, Miradi file or directly in Insight

The monitoring report requires the project team (and key partners/stakeholders where possible) to systematically review and discuss data/information, and identify progress against planned goals and objectives, using associated indicators.

WHAT SHOULD YOU DO

- The monitoring report complements the narrative report. Consider which results should be highlighted in your Part 1 narrative, for example because they could be scaled/ replicated across the country or Network, or because management support (or a shift in strategy) may be required to make better progress.

- Prepare your monitoring report by updating the columns with titles in red (see Table 2). The Monitoring Report table should contain goals and objectives from your latest strategic plan (not your annual work plan), their related indicators, baseline and Planned Intermediate Result (PIR). Make sure that the planned PIRs indicate clear progress towards achievement of the objective (and reference indicators where possible), and can hence suggest whether the theory of change is working.

- Score your progress towards achieving the selected long term results against the conservation achievement KPI rating (see the rating scale below). The rating should be made in relation to your annual planned intermediate results (PIRs) for the current year as well as the long term results. It is important for the project/ programme team to use its judgment and to be as objective as possible. Ratings range from 1 to 5, and fractional ratings are also possible, for example, a rating of 3.5. Note that where a PIR has been achieved it could be rated anywhere from 3 to 5; ratings of 4 or 5 should be given only where strong evidence can also be shown towards the goals (impact) or the long term objectives (outcomes).

- Provide a justification for your ratings. This serves to clarify the evidence for your rating and for your result. The ratings should be useful to both team and management.

- Calculate an overall conservation achievement rating for the project/programme based on a simple average (arithmetic mean) of the individual scores for the objectives that you have included. You may also provide ratings for progress towards the goals (this is optional).

- Provide more detailed information if you think this is useful e.g. attach or provide a link to additional monitoring data, graphs, diagrams, reviews or evaluations.

Table 2. Monitoring Report

| Goals/ Impact Good goals are SMART and normally linked to biodiversity or human wellbeing | Indicator (what is being measured) and the units | Baseline (value & date) | Planned Intermediate Result (PIR) (“What result the project planned to achieve by this time”) |  |  |  |  | Current status this year (“what result was achieved by the time of this report”) Columns in red indicate information specific to the TPR | Planned Final Result (value & date) |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | FYxx |  | FYxx |  | FYxx |  |  |  |  |
| Columns in black indicate information to draw directly from your monitoring plan |  |  |  |  |  |  |  | Where no new data available, state when next measurement due. Did the current status meet the planned result? |  |  |  |
| Key Long-term Objectives (Outcomes) | Indicator (what is being measured) and the units | Baseline (value & date) | Planned Intermediate Result (“what result the project planned to achieve by this time”) |  |  |  |  | Current status this year (“what result was achieved by the time of this report”) | Planned Final Result (value & date) | Conservation Achievement Rating How did you choose the rating that you gave? | Justification(s) for rating |
|  |  |  | FYxx | FYxx |  | FYxx What are the milestones you intend to reach to achieve the objective? PIRs are needed to help track progress against long-term objectives. |  |  |  |  |  |
| These should be based on what is in your strategic plan |  |  |  |  |  |  |  |  |  |  |  |
| Overall Conservation Achievement Rating (based on long-term objectives) |  |  |  |  |  |  |  |  |  |  |  |

Scoring Guidelines for Conservation Achievement KPI ratings

New TPR Part 2 rating scale

Ratings systems can make a useful contribution to reflection and communication of progress. The rating system should:

- Be objective, based on data and/ or criteria

- Provide an indication of progress (or not) towards the planned result

- Be informed by an assessment of progress vs the planned result(s)

- Help indicate where management should pay attention

- Preferably be against one unified scale

5 - Achieved (>80%) --> Opportunity. The goal or long term objective has been achieved (>80%), and there is good evidence to demonstrate this. There may be opportunities to communicate and/or replicate the success across the country or region or the Network.

4 - Well Advanced/ Strong Progress (50-80%). The planned intermediate result (PIR) for the current FY has been entirely met (or almost) and monitoring evidence demonstrates strong progress (50-80% of the way) towards the long term objective.

3 - On Track/ Progress (<50%) The planned intermediate result (PIR) for the current FY has been entirely met and suggests the project is ‘on track’ towards the long-term objective. However the demonstrated progress towards the long term objective is <50% and/ or the monitoring evidence is weaker. Any issues are minor and are being addressed by the relevant team.

2 - Partially Achieved, some barriers. There were moderate shortcomings in the achievement of the PIR for the current FY. There may be barriers to implementation (e.g. partner engagement) may have recently presented, but these barriers can be addressed by relevant teams alone.

1 - Not Achieved, Support needed. The achievement of the PIR for the current FY is very low AND/OR significant barriers to achievement of the result may have recently occurred. May require immediate management attention to address one or more internal or external factors that will substantially limit or prevent the achievement of the result. Where issues cannot be resolved, a shift in strategy may be required.

Not Yet Progress against the result was not possible or was not expected this year, but looking ahead no major barriers are foreseen.

Not Known. No data is available to enable an assessment

Note that some of these examples used previous versions of this TPR format.

Theory of change is often expressed in the form of a diagram such as a Results Chain that clarifies the project’s logic, combined with a statement of an overarching approach or philosophy that the project considers to be ‘true’. A logframe or similar results framework can be an alternative format.